## High Level Plan - Generic
Current Sprint - T
Activity | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Sprint Planning | Morning Session - 4 Hrs
Daily Stand Up |  | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins | Morning 15 Mins
Prep Meetings for T + 2 |  |  | Afternoon - 1 Hr |  |  | Afternoon - 1 Hr |  | Afternoon - 1 Hr
Refinement Sessions for T + 1 |  |  |  | Afternoon - 1 Hr |  | Afternoon - 1 Hr |  | Afternoon - 1 Hr
Check Point / Sign Off (Day Before Sprint ends) | [8 empty] | Morning - 1 hr
Sprint Review | [9 empty] | Afternoon- 2 Hrs
Sprint Retrospective | [9 empty] | Afternoon- 2 Hrs
Sprint Planning (Ownership - PO / Acting Scrum PO) | Parties Involved | Input to Session | Output |  | Time Line Commitments for Various Ceremoines
[5 empty] | Role | Time Commitment / Sprint
| PO / Acting Scrum PO | Agreed JIRA Stories | Story Point Estimates - Finalized |  | PO | 17 Hrs
| Scrum Master | Design Completed | Committed Stories |  | Scrum Master | 17 Hrs
| Development Team | Screens agreed | Blockers Identified |  | Development Team | 14 Hrs
| Business Owners - If required | Dependencies Identified | Story level tasks |  | Other Stakeholders | 13 Hrs
| Other Stakeholder as required | Defect Stories | Estimates for Story level task |  | All - Others | 2 Hrs + As and when required
Technical / POC Stories
Daily Stand Up (Ownership - Team / SM) | PO | Story level tasks | Status of Story level tasks
| Scrum Master |  | Blockers
| Development Team |  | New tasks identified
Prep Meetings (Ownership - PO / Business Owners) | PO | Stories for T + 2 Sprints | Status of Various activities, as per flow of work by stakeholders
| Scrum Master |  | Dates committed
| Business Owners |  | DoR - Sign Off
Other Stakeholder as required - Solution Design / Arch. / UI / UX
User Story Refinement - Functional Sessions (Ownership - PO) | PO | Stories for T + 1 sprint | Blockers Identified
| Scrum Master | Design Completed | Story Point Estimates
| Development Team | Screens agreed | Queries on the new stories
| Business Owners - If requried | Dependencies Identified | Impact of new stories on other work if any
| Other Stakeholder as required |  | Splitting of uer stories - If required
Technical stories - Identified
Change of prioritization and DoR Final Sign Off
User Story Refinement - Technical Sessions (Ownership - Technical Lead) | Technical lead | Stories for T + 1 sprint | Blockers Identified
| PO | Design Completed | Technical Discussions
| Scrum Master | Screens agreed | Queries on the new stories
| Development Team | Dependencies Identified | Impact of new stories on other work if any
Business Owners - If requried
Other Stakeholder as required
Checkpoint / Sign Off Meeting (Ownership - PO) | PO | Stories Ready | PO to review and Sign off the User stories as completed
| Scrum Master | Development Cycle 90% completed | Highlight Issues
| Development Team |  | Team ready for the final demo
DoD - Sign Off
Sprint Demo (Ownership - Team / Scrum Master) | PO | Status of the current sprint | Demo - Completed
| Scrum Master | Metrics on current sprint | New Stories / Functions identified
| Development Team | Demo of the completed stories | Achieved Velocity
| Business Owners |  | Direction on the Product / Features
| Other Stakeholder as required |  | Defects
| All other Invities - Special Ones |  | New Changes to current stories
Defects and others documented in JIRA
Sprint Retrospective (Ownership - SM / Team) | PO | Demo - Completed | Plus and Minus identified
| Scrum Master | Previous Retrospective Data | Previous Retro items discussed
| Development Team |  | New items added to the Retro Backlog

## Cadence Planning
SPRINT EXECUTION PLAN AND CADENCE
Timeline | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
10:00 - 10:30 | Sprint Planning - All teams members Supported by PO / Business
10:30 - 11:00
11:00 - 11:30 |  | Daily Scrum | Daily Scrum | Daily Scrum | Daily Scrum | Daily Scrum | Daily Scrum | Daily Scrum | Daily Scrum | Daily Scrum
11:30 -12:00
12:00 - 12:30 |  |  | Prep Meetings - PO & Scrum Master | User Story Refinement - Functional (For the next Sprint)
12:30 -13:00
13:00 -13:30 | [6 empty] | User Story Refinement - Technical (For the next Sprint) |  | Checkpoint Demo
13:30 -14:00
14:00 - 14:30 | [9 empty] | Sprint Review
14:30 - 15:00
15:00 - 15:30
15:30 - 16:00
16:00 - 16:30
16:30 - 17:00 | [9 empty] | Retrospective - All Teams
17:00 - 17:30
17:30 - 18:00